## Renew-Replace Schedule
CIP FY | 2011 | Building System Appraisal (List taken from Appendix A of EED Preventive Maintenance Handbook) |  |  | Current Dollar Value of Systems/Components that require Renewal or Replacement during Year (in thousands of dollars) | [6 empty] | Deferred Project | Attach Survey if included in CIP | Total Costs by System (in dollars)
Facility or Building |  | System | Year Installed | Remain-ing Life Span | Year work req'd | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
Name and/or Number |  | Site Improvements |  |  |  | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
EED # |  | Site Utilities
Dist. # |  | Foundation/Substruct.
Superstructure
Gross Square Footage |  | Exterior Wall System
Exterior Windows
Exterior Doors
Number of Stories |  | Roof Systems
Interior Partitions
Interior Doors
Building or Facility Use |  | Interior Floor Finishes
Interior Wall Finishes
Interior Ceiling Finishes
Replacement Value |  | Specialties
Conveying Systems
Plumbing piping
NOTES |  | Plumbing Fixtures
Fire Protect./Suppres.
HVAC Distribution
HVAC Equipment
HVAC Controls
Electrical Serv./Gen.
Electrical Distribution
Electrical Lighting
Special Electrical
Facility Cost Index |  | Equip and Furnishings
|  | Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Six Year Total
Instructions for completion:
1. Enter data into green shaded areas beginning with cell B1.
2. Only complete "year installed" if the system exists in the facility.
3. If 50% or more of a system is renewed, update the year installed.

## Data
System
| Life Expect | % cost 1-story | % cost 2-story | 1 STORY |  | 2 STORY
|  |  |  | Means | K-12 | Means | K-12
Site Improvements | 25 | n/a | n/a
Site Utilities | 40 | n/a | n/a
Foundation/Substruct. | 50 | 10.25% | 5.78% | 11.2% | 9.3% | 7.5% | 4.06%
Superstructure | 50 | 13.63% | 16.57% | 9% | 18.26% | 15.3% | 17.84%
Exterior Wall System | 25 | 9.095% | 7.49% | 5.3% | 12.89% | 6% | 8.98%
Exterior Windows | 30 | 2.405% | 2.588% | 3.7% | 1.11% | 3.956% | 1.22%
Exterior Doors | 20 | 0.4797% | 0.4411% | 0.5994% | 0.36% | 0.4222% | 0.46%
Roof Systems | 20 | 4.64% | 5.09% | 5.4% | 3.88% | 3.5% | 6.68%
Interior Partitions | 50 | 5.265% | 5.28% | 4.8% | 5.73% | 4.5% | 6.06%
Interior Doors | 30 | 1.632% | 1.725% | 1.264% | 2% | 1.22% | 2.23%
Interior Floor Finishes | 15 | 5.45% | 5.613% | 7.4% | 3.5% | 7.365% | 3.86%
Interior Wall Finishes | 25 | 2.074% | 2.17% | 2.398% | 1.75% | 2.2% | 2.14%
Interior Ceiling Finishes | 25 | 3.483% | 3.225% | 5.216% | 1.75% | 5.2% | 1.25%
Specialties | 40 | 2.663% | 2.944% | 0.8262% | 4.5% | 0.8288% | 5.06%
Conveying Systems | 40 |  | 0.38% |  |  | 0.5% | 0.26%
Plumbing piping | 30 | 3.5% | 3.645% | 4% | 3% | 3.9% | 3.39%
Plumbing Fixtures | 30 | 1.715% | 1.54% | 1.8% | 1.63% | 1.8% | 1.28%
Fire Protect./Suppres. | 30 | 2.565% | 2.735% | 2.2% | 2.93% | 1.9% | 3.57%
HVAC Distribution | 40 | 5.05% | 5.25% | 3.1% | 7% | 3% | 7.5%
HVAC Equipment | 30 | 11.43% | 10.75% | 18% | 4.86% | 17.1% | 4.4%
HVAC Controls | 20 | 2.15% | 2.495% | 1.3% | 3% | 1.2% | 3.79%
Electrical Serv./Gen. | 40 | 2.035% | 2.677% | 0.5% | 3.57% | 0.7037% | 4.65%
Electrical Distribution | 50 | 2.445% | 2.76% | 1.5% | 3.39% | 1.5% | 4.02%
Electrical Lighting | 25 | 5.59% | 6.05% | 8.5% | 2.68% | 8.5% | 3.6%
Special Electrical | 15 | 2.455% | 2.8% | 2% | 2.91% | 1.9% | 3.7%
Equip and Furnishings | 25 | n/a | n/a
|  | 100% | 100% | 100% | 100% | 100% | 100%

## Sample Renew-Replace Schedule
CIP FY | 2011 | Building System Appraisal (List taken from Appendix A of EED Preventive Maintenance Handbook) |  |  | Current Dollar Value of Systems/Components that require Renewal or Replacement during Year (in thousands of dollars) | [6 empty] | Deferred Project | Attach Survey if included in CIP | Total Costs by System (in dollars)
Facility or Building |  | System | Year Installed | Remain-ing Life Span | Year work req'd | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
Name and/or Number |  | Site Improvements |  |  |  | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
EED # | xxxxxxxx | Site Utilities
Dist. # | xxxx-xxx | Foundation/Substruct. | 1995 | 34 | 2045 | [8 empty] | 737065.6
|  | Superstructure | 1995 | 34 | 2045 | [8 empty] | 2113006.4
Gross Square Footage |  | Exterior Wall System | 1995 | 9 | 2020 | [8 empty] | 955124.8
106197 |  | Exterior Windows | 1995 | 14 | 2025 | [8 empty] | 330035.519
|  | Exterior Doors | 1995 | 4 | 2015 | Year 4 2014: 56.2494 |  |  | 56249.3811
Number of Stories |  | Roof Systems | 1995 | 4 | 2015 | Year 4 2014: 649.0768 |  |  | 649076.8
2 |  | Interior Partitions | 1995 | 34 | 2045 | [8 empty] | 673305.6
|  | Interior Doors | 1995 | 14 | 2025 | [8 empty] | 219953.0565
Building or Facility Use |  | Interior Floor Finishes | 1995 | -1 | 2010 | Year 1 2011: 715.7142 | X |  | 715714.2255
Alaska Elementary School |  | Interior Wall Finishes | 1995 | 9 | 2020 | [8 empty] | 276718.4
|  | Interior Ceiling Finishes | 1995 | 9 | 2020 | [8 empty] | 411252
Replacement Value |  | Specialties | 1995 | 24 | 2035 | [8 empty] | 375468.1332
12752000 |  | Conveying Systems | 1995 | 24 | 2035 | [8 empty] | 48457.6
|  | Plumbing piping | 1995 | 14 | 2025 | [8 empty] | 464810.4
NOTES |  | Plumbing Fixtures | 1995 | 14 | 2025 | [8 empty] | 196380.8
|  | Fire Protect./Suppres. | 1995 | 14 | 2025 | [8 empty] | 348767.2
|  | HVAC Distribution | 1995 | 24 | 2035 | [8 empty] | 669480
|  | HVAC Equipment | 1995 | 14 | 2025 | [8 empty] | 1370840
|  | HVAC Controls | 1995 | 4 | 2015 | Year 4 2014: 318.1624 |  |  | 318162.4
|  | Electrical Serv./Gen. | 1995 | 24 | 2035 | [8 empty] | 341350.3018
|  | Electrical Distribution | 1995 | 34 | 2045 | [8 empty] | 351955.2
|  | Electrical Lighting | 1995 | 9 | 2020 | [8 empty] | 771496
|  | Special Electrical | 1995 | -1 | 2010 | Year 1 2011: 357.056 | X |  | 357056
Facility Cost Index |  | Equip and Furnishings
0.084126 |  | Totals |  |  |  | 1072.7702 | 0 | 0 | 1023.4886 | 0 | 0 | 2096258.8066 |  | Six Year Total